## Tabelle1
First Website to show the idea of the webapp | Spalte1 | Spalte2 | At First i want to gife a idea what the produkt should be about, with very little features, just usefull info text to use in a daily WG life | Spalte3 | Spalte4 | Spalte5 | Spalte6 | Spalte7
ID | Prio | Epic | User-Story | Criteria of Satisfaction | Effort | Done?
1000 | 1 | Designe of FirstPage | As a "Company" i want that the first page catches the user, that the user want to work more with this webside Want to have a clear vision of the designe of the website in order to offer my customers that they love the tool | prototype of the starter page and sketch | 5 | Yes
1001 | 2 | Designe of FirstPage | Find some good titels for the sub pages (in the buttons) make a sketch for the list fields and add them to the first page | the designe of the first page should be finished, the user should understand what the website is about without looking into the sub pages, the sketches for the lists should give an idea how the tools work | 3 | Yes
1066 | 3 | Log-in-Page | the log in page should look good, as a user I should understand how i log in in order to get execes to the website (when a user is existing) | user input field, password input field, message when user name/password is wrong | 2 | Yes
1087 | 4 | Log-in-Page | learn and write the logic | you should be able to log in with an existing user (123 123) | 5 | Yes
1002 | 5 | FirstPage | Add the links from the sub pages to the buttons | As a user i want to be able to navigate from every page to every page | 2 | Yes
| 6 | sub-site/ Lists | designe | all buttons for the sub sites should be visible and the whole site should be structures and designed | 3 | Yes
1027 | 7 | third Sub-Site/ Plants | Logic for add items/delete | you should be able to add new items (plants) and write important infos about them | 5 | Yes
1029 | 8 | third Sub-Site/ Plants | find some plants to add them as defoult | find the names of your housplants and the important infos and add them to the sub page | 2 | Yes
1030 | 9 | third Sub-Site/ Plants | find some pics for the plants | find some pics to the added plants | 1
1030 | 10 | third Sub-Site/ Plants | finish the page | as a user i want to see a usefull and understandable page with nice features and no fisible bugs, it should look like a finished professiolal page | 2
1011 | 11 | FirstPage (animation is needed till 13.06.2024 for the project) | Designe the Plants button, with a picture and some animations(also dmake a scatch how the animation should look like) | The plants button should have a nice background and when you hover over it, some plants should grow out of the button. As a user i want to be impressed about the sudden animation and want to see it over and over again, it should make joy but dose not have more use | 5
1020 | 12 | secound Sub-Site/ Food | Designe | The sub site should have a good structure and good colors, button to add and delete things should be added and a back button to the home page | 3
1026 | 13 | third Sub-Site/ Plants | Designe | The sub site should have a good structure and good colors, button to add and delete things should be added and a back button to the home page | 3
1014 | 14 | first Sub-Site/ Projects | Designe | The sub site should have a good structure and good colors , button to add and delete things should be added and a back button to the home page | 3
1015 | 15 | first Sub-Site/ Projects | Logic for create items | you should be able to add a item ( projects) and add the important information in it how to finish it | 3
1021 | 16 | secound Sub-Site/ Food | Logic for add items/delete | you should be able to add a item ( a resepie) and add the important information in it how to cook it | 3
1023 | 17 | secound Sub-Site/ Food | find some recepies to add them as defoult | some resepies should be added to have some ideas how the page is structured | 3
1024 | 18 | secound Sub-Site/ Food | find some pics for te resepies | some pics should be added to the generated menues | 1
1036 | 19 | fourth sub site:Lists/ sub sub site: "Einkaufsliste | Designe | The sub sub site should have a good structure and good colors, button to add and delete things should be added and a back button to the home page and one to go back one site | 2
1042 | 20 | fourth sub site: Lists/sub sub site"Putzplan" | Designe | The sub sub site should have a good structure and good colors, button to add and delete things should be added and a back button to the home page and one to go back one site | 2
1046 | 21 | fourth sub site: Lists/ sub sub site "Essplan" | Designe | The sub sub site should have a good structure and good colors, button to add and delete things should be added and a back button to the home page and one to go back one site | 2
1051 | 22 | fourth sub site: Lists/sub sub site "To do list" | Designe | The sub sub site should have a good structure and good colors, button to add and delete things should be added and a back button to the home page and one to go back one site | 2
1037 | 23 | fourth sub site:Lists/ sub sub site "Einkaufsliste" | Logic for add items/delete | you should be able to add new items | 3
1043 | 24 | fourth sub site: Lists/sub sub site "Putzplan" | Logic for add items/delete | you should be able to add new items | 3
1047 | 25 | fourth sub site: Lists/sub sub site "Essplan" | Logic for add items/delete | you should be able to add new items | 3
1052 | 26 | fourth sub site: Lists/sub sub site "To do list" | Logic for add items/delete | you should be able to add new items | 3
1003 | 27 | FirstPage | Add the preview of the To Do list to the first page | You should see the ToDos in a smal window | 5
1005 | 28 | FirstPage | Add the preview of the "Putzplan" to the first page | You should see the tasks of the Putzplan | 5
1006 | 29 | FirstPage | Add the preview of the Shopping list to the first page | you should see the shopping list | 5
1007 | 30 | FirstPage | Add the preview of the Food list to the first page | you should see the planed meals | 5
1055 | 31 | fourth sub site: Lists/ sub sub site "Essplan" | link the existing menues from the Food sub site | you should be able to link the correct menu | 8
as a user i want to see what are the tasks for today without navigating throu the website
die person asprechen mit as a …......
You can ignore the rest
____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________
New Features with the Web App
1034 | ? | Lists/ "Einkaufsliste"
1032 | ? | Sport | Designe
1033 | ? | Sport | Logic for add items/delete
1017 | ? | Projects | logic for "visible for group members/ editable for group members"
1016 | ? | Projects | sub site for the items, designe and logic for the input fields and check if finished
1022 | ? | Food | logic for open up the resepie in the same page and close it
1025 | ? | Food | logic for a "kalorien Rechner"
1028 | ? | Plants | logic for open up the info about the plant in the same page and close it
1003 | ? |  | Add the preview of the To Do list to the first page | The to do list should be usable on the first page with some(not all) options like in the sub page of the to do list. The designe should be like in the sketch bevore of the to do list. You should be able to see the to dos from the sub page and you should be able to delete some entries when you finished them
1004 | ? | FirstPage | Add the logic to the placeholder of the AI daily phrases and make the footer and header fix when you scroll | the logic should be finished and the tool should be able to write some random phrases. When you scroll the footer should be fix and the header should get smaler and be fix
1005 | ? | FirstPage | Add the preview of the "Putzplan" to the first page | The Putzplan should be usable on the first page with some(not all) options like in the sub page of the putz plan. The designe should be like in the sketch bevore. You should see the tasks and you should be able to tick off the tasks, the tick of should be removed when a new week begins
1004 | ? | FirstPage | Add the logic to the placeholder of the AI daily phrases and make the footer and header fix when you scroll | the logic should be finished and the tool should be able to write some random phrases. When you scroll the footer should be fix and the header should get smaler and be fix
First Steps With mobile App
1036 |  | Lists/ "Einkaufsliste
1037 |  | Lists/ "Einkaufsliste"
1038 |  | Lists/ "Einkaufsliste"
1039 |  | Lists/ "Einkaufsliste"
Lists/ "Einkaufsliste"
1042 |  | Lists/"Putzplan"
1043 |  | Lists/"Putzplan"
1044 |  | Lists/"Putzplan"
1045 |  | Lists/"Putzplan"
1046 |  | Lists/ "Essplan"
1047 |  | Lists/ "Essplan"
1048 |  | Lists/ "Essplan"
1049 |  | Lists/ "Essplan"
1050 |  | Lists/ "Essplan"
1051 |  | Lists/"To do list"
1052 |  | Lists/"To do list"
1053 |  | Lists/"To do list"
1054 |  | Lists/"To do list"
1055 |  | Lists/"To do list"
1056 |  | WG Dokumente
1064 |  | Einstellungen
1041 |  | Einstellungen | Farbe einstellen und optionale tools
1066 |  | Einstellungen
1067 |  | Einstellungen
1068 |  | Log in Page
1069 |  | Log in Page
1070 |  | Date and "Anwesenheit"
1071 |  | "Restgeld"
1072 |  | "Restgeld"
1034 |  | Sport | logic for open up the info about the sport in the same page and close it
|  | Sport | find some sports to add them as defoult
|  | Sport | logic for check list for sport activities per day/per week
|  | Sport | link some home exercises videos
1082 |  | Sport | create a whole sports app into this app
1083 |  | Sport
1084 |  | Sport
1085 |  | Sport
1086 |  | Sport
1087 |  | Drinking games | Drinking games
1090
1091
1092
1093
1094
1095
1096
1097
1098
1099
1100
1101
1102
1103
1104
Website fith more features
1006 |  | FirstPage | Add the preview of the Shopping list to the first page | you should see the things to buy, you should be delete the bought things and you should be able to fast add additional things
1007 |  | FirstPage | Add the preview of the Food list to the first page | you should see the planed food for the week and cross out the made things, the plan should be reloded after a week
1010 |  | FirstPage | Add the preview of the "Restgeld" to the first page | you should see the "restgeld" from the sub page
1009 |  | FirstPage | Add the preview of the "Datum und Anwesenheit" to the first page | you should the the correct date and what peaople are planed to be at home on the date
1010 |  | FirstPage | Add the preview of the "Restgeld" to the first page | you should see the "restgeld" from the sub page
1009 |  | FirstPage | Add the preview of the "Datum und Anwesenheit" to the first page | you should the the correct date and what peaople are planed to be at home on the date
1122
1123